## Burndown Chart
Sprint 1 Burndown Chart
Task ID | Task Description | Initial Estimate | 2022-10-17 | 2022-10-18 | 2022-10-19 | 2022-10-20 | 2022-10-21
|  | Day 0 | Day 1 | Day 2 | Day 3 | Day 4 | Day 5
1 | Preparation of the "workplace" | 2 |  | 1 | 1
2 | Identifie GoF design patterns | 2 |  |  |  | 0.4
3 | Identifie code smells | 2 |  |  | 0.4
4 | Review each others work | 1
5 | Make report | 1
Completed Effort |  | 0 | 0 | 1 | 1.4 | 0.4 | 0
Remaining Effort |  | 8 | 8 | 7 | 5.6 | 5.2 | 5.2
Ideal Burndown |  | 8 | 7.4667 | 6.9333 | 6.4 | 5.8667 | 5.3333